## Sheet1
PHANST - Event Management Services
ID.NO | Rank | Risk | Description | Category | Triggers | Potentiial Responses | Risk Owner | Probablity | Impact | Status
1 | 2 | Infrastructure Assistance | It's possible that the new infrastructure won't work with the old one. | Maintance | Service outage | Test Before intergation. | Pravallika Maddelavede | High | High | Open
2 | 3 | Server Assistance | It's possible that the server won't be able to handle a bigger number of users. | Maintance | Application hang or slow response | Increase server capacity. | Anusha Bandari | Meduim | Medium | Open
3 | 1 | More Flaws in the Platform | The application development platform is riddled with flaws. | Design | Bad user experience | Need more design and testing. | Harshitha Dandyala | High | High | Open
4 | 6 | Client Assistance | Clients may not be willing to assist with needs during development. | Executive | Poor feature developnment | Make frequent meetings with clients. | Navya Sri Alaparthi | Medium | Medium | Open
5 | 4 | Exapnsion of the Creep | As the platform is updated on a regular basis, the scope of this project may change. | Scope | Poor scope developnment | Communicate with client for time to time updates and changes. | Sravani Kodipelly | Medium | Medium | Open
6 | 5 | Experiences of Users | Users may not like the graphical interface. | Design | Bad user experience | Need cutomer feedback. | Tejaswi Gannamaneni | Medium | High | Open