## Sheet1
Project Name:PHANST-Event Management Services |  | Date:03-29-2022 |  | Prepared By: Anusha Bandari,Tejaswi Gannamaneni
Task | Start Date | End Date | Working Days | Days | Task
1.Initiating | 2022-01-26 | 2022-02-04 | 8 | 9 | 1
2.Planning | 2022-02-07 | 2022-02-18 | 10 | 11 | 2
3.Communications | 2022-02-21 | 2022-03-04 | 10 | 11 | 3
4.Main Deliverables | 2022-03-07 | 2022-03-18 | 10 | 11 | 4
5.Monitoring and Controlling | 2022-03-21 | 2022-04-08 | 15 | 18 | 5
6.Closing | 2022-04-11 | 2022-04-29 | 15 | 18 | 6
1.Initiating
2.Planning
3.Communications
4.Main Deliverables
5.Monitoring and Controlling
6.Closing